## Document History
Document History
Version | Who | When | What
1.0.0.0 | Mahantesh S.H | 15/02/2015 | Design
1.0.0.1 | Vinay S.P | 20/02/2015 | Review

## ManageTest
Project name: | SpaceCenter |  | Test case type:
Module Name: | Medical Panel |  | Operating System: Windows 10 Pro
Sub-module Name: | Biomedical Monitoring tab |  | Original Author: Ryan Ursonal
Objective: |  |  | Reviewed By:
Browser:
Original date : | 2016-10-25
Test Case ID | Business Logic | Role | Steps for Execution | Expected Results | Pass / Fail DOE | Tester | Remarks
1 | Determining if there is a Biomedical monitoring event in master | FD | Load a biomedical report in start to-do tab in core and start doing the steps in master. Then check the "BM" button in core if it turns to red. | the "BM" button should turn to red color and will go back to its original color, when it is clicked. | Failed | Zachary | BM button doesn’t turn ren even all task is complete
2 | Biomedical display | FD | Load a biomedical report in start to-do tab in core | Check for the display of selected biomedical report | Pass | Zachary
3 | Mark the steps as completed | FD | Complete each steps in master and check the step list in core | completed steps should turn to green | Pass | Zachary
4 | Showing the steps of the selected Biomedical report | FD | Click any of the selected Biomedical report | It should display the steps of the selected Biomedical report and the status of every steps if its completed or not inside the lower box | Pass | Zachary
5 | Marking the Biomedical report list as completed | FD | Complete the steps in Biomedical report in the master and check the Biomedical list and its steps if it is marked as completed | Every steps of Biomedical report should turn to green, and should mark the Biomedical report list as completed. | Pass | Zachary
6 | complete button functionality | FD | Click the complete button on the right side of every steps in Biomedical report | it should change the status of every steps into completed and will mark the Biomedical report as completed when all of the steps is already completed. | Pass | Zachary
7 | Biomedical ToDo List Detail should be updating | FD | Complete an item in the Biomedical ToDo List | The Biomedical ToDo List Detail should be updated without user clicking the Biomedical ToDo List